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Draft timeline for the catastrophe risk work stream (CAT WS) of EIOPA's SCR Review Project

	Date
	Event
	Comments / aim

	23 Mar ‘17
	Telecon
	First telecon with the CAT WS. Explanations of the organisation of the work and its timing.

	6/7 Apr ‘17
	Input to PG
	Input from stakeholders on potential recalibration areas/topics (to be received before 29 Mar ’17) will be prioritised and subsequently submitted to the SCR review Project Group

	27 Apr ‘17
	1st physical meeting
	Presentation of proposals for
- simplifications
- priorities for recalibration 
"Carry-forward": finalise simplifications first, then tackle recalibration areas/topics according to prioritisation -> if a sub-topic cannot be concluded, it could be carried forward once to next telecon/meeting with the clear view to solve it; topics that turn out to be controversial should be escalated to the SCR PG or even IPC level after having been carried forward once, accompanied by necessary information (options considered, pros and cons for each option);
finalised topics: subsequent submission of results to SCR PG

	18 May ‘17
	2nd physical meeting
	See above

	22 Jun ‘17
	3rd physical meeting
	See above

	13 Jul ‘17
	4th physical meeting
	Preparation of documents according to progress of discussion on the topics

	mid Jul ‘17
	Sub-mission DL
	Data from the annual QRT received. Will allow to test proposals and assess their impact on the European market

	24 Aug ‘17
	5th physical meeting
	Discussion on the outcome of the NatCat data testing;
carry forward from 13 Jul ’17 meeting

	11 Sep ‘17
	IPC meeting
	Presentation of the calibrations and impact assessment by EIOPA staff

	14 Sep ‘17
	6th physical meeting
	Last physical meeting before dedicated BoS meeting on 26 Oct ‘17

	26 Oct ‘17
	BoS meeting
	Discussion/decision on Consultation paper

	05 Jan ‘18
	Submis-sion DL
	End of 8 week consultation period (to be started on 3 Nov 2017); start resolution of received comments

	11 Jan ‘18
	Telecon
	Discussion on final Technical Advice

	25 Jan ‘18
(poss. 26 Jan ’18 – when needed)
	7th physical meeting
	Last physical meeting before dedicated BoS Meeting on 27 Feb ‘18

	end Feb ‘18
	BoS meeting
	Discussion/decision on final Technical Advice

	28 Feb ‘18
	Submis-sion to EC
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