Select Information Classification Levels. If PUBLIC please select blank

EIOPA-17/155
21 Mar 2017

Draft timeline for the catastrophe risk work stream (CAT WS) of EIOPA's SCR Review Project

| Date | Event | Comments / aim |
| --- | --- | --- |
| 23 Mar ‘17 | Telecon | First telecon with the CAT WS. Explanations of the organisation of the work and its timing. |
| 6/7 Apr ‘17 | Input to PG | Input from stakeholders on potential recalibration areas/topics (to be received before 29 Mar ’17) will be prioritised and subsequently submitted to the SCR review Project Group |
| 27 Apr ‘17 | 1st physical meeting | Presentation of proposals for - simplifications - priorities for recalibration "Carry-forward": finalise simplifications first, then tackle recalibration areas/topics according to prioritisation -> if a sub-topic cannot be concluded, it could be carried forward once to next telecon/meeting with the clear view to solve it; topics that turn out to be controversial should be escalated to the SCR PG or even IPC level after having been carried forward once, accompanied by necessary information (options considered, pros and cons for each option); finalised topics: subsequent submission of results to SCR PG |
| 18 May ‘17 | 2nd physical meeting | See above |
| 22 Jun ‘17 | 3rd physical meeting | See above |
| 13 Jul ‘17 | 4th physical meeting | Preparation of documents according to progress of discussion on the topics |
| mid Jul ‘17 | Sub-mission DL | Data from the annual QRT received. Will allow to test proposals and assess their impact on the European market |
| 24 Aug ‘17 | 5th physical meeting | Discussion on the outcome of the NatCat data testing; carry forward from 13 Jul ’17 meeting |
| 11 Sep ‘17 | IPC meeting | Presentation of the calibrations and impact assessment by EIOPA staff |
| 14 Sep ‘17 | 6th physical meeting | Last physical meeting before dedicated BoS meeting on 26 Oct ‘17 |
| 26 Oct ‘17 | BoS meeting | Discussion/decision on Consultation paper |
| 05 Jan ‘18 | Submis-sion DL | End of 8 week consultation period (to be started on 3 Nov 2017); start resolution of received comments |
| 11 Jan ‘18 | Telecon | Discussion on final Technical Advice |
| 25 Jan ‘18 (poss. 26 Jan ’18 – when needed) | 7th physical meeting | Last physical meeting before dedicated BoS Meeting on 27 Feb ‘18 |
| end Feb ‘18 | BoS meeting | Discussion/decision on final Technical Advice |
| 28 Feb ‘18 | Submis-sion to EC |  |